# Pelagos_CST18_2026_Doc04

# English/French/Italian

# Distribution: 03/05/2026

Draft Doc. 04

# Pelagos Congress 2028

### First Triennial Congress of the Pelagos Sanctuary

# Draft Doc4

# Integrated Proposal

# Pelagos Congress 2028

### First Triennial Congress of the Pelagos Sanctuary

## 1. Executive Summary

It is proposed to establish the Pelagos Congress as the official recurring congress of the Pelagos Sanctuary, to be held every three years.

The first edition in 2028 would be strategically timed to coincide with:

- completion of the Management Plan 2022–2027

- launch of the new Management Plan 2028–2033

- renewal of stakeholder engagement

- stronger trilateral visibility for France, Italy and Monaco

This would create a permanent governance milestone for the Sanctuary.

# 2. Strategic Purpose

The Congress should become:

- the flagship political and technical gathering of the Sanctuary

- the formal review moment for each management cycle

- the platform for stakeholder consultation

- a high-level communication tool

- a recurring mechanism for continuity and accountability

# 3. Frequency

## Every 3 years

- 2028 – First Edition

- 2031 – Second Edition

- 2034 – Third Edition

(rotation possible among Parties)

# 4. Why 2028

## Perfect Institutional Timing

2028 marks:

### Closing Phase

Management Plan 2022–2027

### Opening Phase

Management Plan 2028–2033

Therefore the Congress becomes the official bridge between two planning cycles.

# 5. Format (2 Days)

## Day 1 – Institutional & Strategic Forum

- Opening Ceremony

- High-Level Session of Parties

- Review of achievements 2022–2027

- Adoption of priorities 2028–2033

- Official reception

## Day 2 – Science & Stakeholder Forum

- Marine mammals conservation

- Shipping & underwater noise

- Fisheries & bycatch

- Sustainable tourism

- NGOs & civil society

- Closing Declaration

# 6. Venue Recommendation

## Preferred Host:

Monaco

Reasons:

- Presidency until the end of 2027

- international visibility

- neutrality and prestige

- strong ocean identity

- accessibility

- potential institutional support

## Potential Venues

- Oceanographic Museum of Monaco

- Fondation Prince Albert II de Monaco

- Yacht Club de Monaco (select sessions / reception)

# 7. Budget Proposal

## Compact High-Level Format

### Total Budget: €100,000

| Category | € |
| --- | --- |
| Venue & logistics | Offered by the hosting country |
| Interpretation (FR/IT/EN) | 20,000 |
| AV / streaming | 15,000 |
| Event management | 15,000 |
| Catering | 18,000 |
| Registration / branding | 7,000 |
| Speaker support | 18,000 |
| Protocol / local transport | 4,000 |
| Contingency | 3,000 |

# 8. Funding Structure

| Source | € |
| --- | --- |
| Contracting Parties / Secretariat | 50,000 |
| Sponsors / private partners | 30,000 |
| Foundations / grants | 20,000 |

# 9. Governance Structure

## Steering Committee

Representatives of:

- France

- Italy

- Monaco

- Secretariat

## Advisory Groups

- Scientific Committee

- Stakeholder Advisory Panel

- Sponsorship / Partnerships group

# 10. Roadmap 2026–2028

## Q4 2026

- approve concept internally

- include in forward planning

## H1 2027

- political consultation among Parties

- create Steering Committee

- confirm budget envelope

## H2 2027

- venue confirmation

- save the date

- sponsorship outreach

## H1 2028

- programme finalisation

- invitations

- communication launch

## H2 2028

### EVENT DELIVERY

# 11. Expected Outputs

- Pelagos Congress Declaration 2028

- Launch of Management Plan 2028–2033

- Stakeholder recommendations

- strengthened political ownership

- roadmap toward 2031 Congress

# 12. Strategic Message

## “Not just an event — a governance instrument.”

The Pelagos Congress would institutionalise continuity, visibility and cooperation every three years.

# 13. Recommendation to the Executive Secretary

Approve in principle the creation of the Pelagos Congress and initiate consultations in 2026 for delivery in 2028.